## Sheet1
Issue Type | Summary | Description | Priority | Assignee | Reporter | Labels | Epic Link | Sprint | Due Date | Component | Status | Risk Level
Epic | User Authentication | Epic for implementing user login, registration, and permissions. | High | Sujan Nepali | Rabins Bhatta | Authentication |  | Initial Setup & User Authenticatio | 2024-12-20 | User Authentication | To Do | High
Story | Implement User Login | Implement login functionality for users to access their tasks. | High | Sujan Nepali | Sujan Nepali | Authentication | User Authentication | Initial Setup & User Authentication | 2024-12-20 | User Authentication | To Do | High
Story | User Registration | Implement registration functionality for new users to sign up. | High | Sujan Nepali | Rabins Bhatta | Authentication | User Authentication | Initial Setup & User Authentication | 2024-12-25 | User Authentication | To Do | High
Task | Task Management UI Design | Design UI for creating, viewing, and managing tasks. | Medium | Rabins Bhatta | Rabins Bhatta | UI, UX | Task Management | Task Management & UI Development | 2024-12-18 | App UI/UX | In Progress | Medium
Bug | Task Creation Not Working | Fix the bug where tasks cannot be created due to missing fields. | High | Rabins Bhatta | Rabins Bhatta | Task Management | Task Management | Task Management & UI Development | 2024-12-15 | Task Management | To Do | High
Task | Data Backup Implementation | Set up automated backups to prevent data loss in the event of failure. | High | Rabins Bhatta | Sujan Nepali | Backup, Security | Data Management | Data Security & Backup | 2025-01-15 | Data Backup & Recovery | To Do | High
Story | Task Assignment Workflow | Implement task assignment workflow for users to receive and track tasks. | High | Sujan Nepali | Sujan Nepali | Task Management | Task Management | Data Security & Backup | 2024-12-25 | Task Management | In Progress | High
Task | User Data Encryption | Implement encryption for user data storage to enhance privacy and security. | High | Rabins Bhatta | Sujan Nepali | Security, Data | User Data | Task Syncing & Cross-Device Support | 2025-01-10 | User Data | To Do | High
Bug | API Response Timeout | Fix the issue where API requests are timing out, causing task delays. | Critical | Sujan Nepali | Rabins Bhatta | API, Performance | API Integrations | Task Syncing & Cross-Device Support | 2024-12-30 | API Integrations | To Do | Critical
Story | Task Syncing Across Devices | Implement real-time syncing of tasks across different devices. | High | Sujan Nepali | Sujan Nepali | Task Management | Task Synchronization | API Integration & Optimization | 2024-12-28 | Task Synchronization | In Progress | High